## Detai
| GOAL | ACTION STEP 1 | DATE DUE | COMPLETED | ACTION STEP 2 | DATE DUE3 | COMPLETED4 | ACTION STEP 3 | DATE DUE4 | COMPLETED2 | ACTION STEP 4 | DATE DUE2 | COMPLETED3 | MEASURABLE OUTCOMES | MEASURABLE OUTCOME | MEASURABLE OUTCOME2 | Column16 | Column17
| GOAL | AS #1 | DATE DUE | COMPLETED | AS #2 | DATE DUE | COMPLETED | AS #3 | DATE DUE | COMPLETED | AS #4 | DATE DUE | COMPLETED | OC #1 | OC #2 | OC #3 | NEEDED RESOURCES | BUDGET IMPLICATIONS
ACCOUNTING & BUDGETING | Continue to develop annual budget in a timely manner, providing several opportunites for public and BOM input. | Plan 2023 schedule for budget setting meetings | 2023-01-03 |  | Hold workshop on preliminary budget | 2023-06-15 |  | Set preliminary budget and levy | 2023-09-15
| Develop strong understanding of MN property tax system and budgetary implications and requirements. | Take LMC course MN Property Tax Basics | 2023-03-03 |  | POLS 3330. Non-Profit Financial Management | 2023 - TBD
| Be able to apply various budget theories to the development of the district annual budget | edX course - Public Financial Management | 2023-03-31 |  | POLS 3330. Non-Profit Financial Management | 2022-12-31
| Continue to assist independent audit firm in annual audit and submit necessary reporting to appropriate bodies. | Upload documents to engagement portal | 2023-04-07 |  | edX course - Public Financial Management | 2023-03-31 | [7 empty] | Completed audit submitted | No findings
| Involve Audit and Finance Committee in audit and budget throughout process | Set initial budget setting meeting | 2023-04-28 |  | Meeting to discuss audit findings | 2023-04-30 |  | Meet to discuss preliminary budget | 2023-05-23
| Project budget out for minimum of five years to ascertain future levies and potential budget shortfalls | Set up worksheet with capabilities | 2023-05-14 |  | Adjust proposed schedules as necessary | Biannualy | [7 empty] | Spreadsheet | Revised schedule
| Update eLink Database | Annual reporting | 2023-03-01 |  | Progress reporting | As required
| Identify grants and maintain database | Ask for Barr's current database | 2023-01-31
| Organize WBIF | Disseminate materials for partners for consideration | 2023-03-01 |  | Hold partner meeting to discuss projects and build consensus | 2023-04-07 |  | Identify project(s) and finalize logisitics with BWSR and panel. | 2023-06-01
| Develop sound understanding of accounting principles | Succesfully complete Accounting Principles 1 at BSU | 2023-08-01
| Work with Audit and Finance Committee to develop policies and practices to improve the efficeincy of, and reduce the likelihood of error in the processing and payment of invoices | Research the use of electronic signatures on checks. | 2023-05-15 |  | Work with legal and accountants to determine employment status of managers and the implications of paying as vendors | 2023-05-15 |  | Work with accountant and A&F Committee to revamp fund balance tables. | 2023-12-31
GOVERNANCE | Compile policies into single manual to be provided to staff, managers, CAC, and website | Search old on-line and paper files to see what exists | 2023-05-01 |  | Work with legal to prepare recommendation for the Governance Committee | 2023-04-15 | [7 empty] | Policy Manual
| Work with Governance Committee and BOM to identify additional policies to implement related to BOM matters | Meet with GC to discuss | 2023-02-01
| Review and suggest edits to Governance Manual | Provide comments to GC | 2022-10-07 |  | Review comments received with legal counsel and GC | 2023-07-01 |  | Deseminate to BOM for review | 2023-07-01 |  | Hold BOM workshop to discuss GC recommended manual revisions | 2023-07-20 |  | Updated governance manual
| Volunteer to serve on MAWD committees | Network | On-going |  | Volunteer | 2023-03-31
| Act as staff representative on the Governance Committee | Work with GC members to set agenda's, develop & disseminate materials, etc | On-going
| Emergency contingency plan - back up | Develop plan outline | 2023-06-01 |  | Present to Personnel Committee for comment and revisions | 2023-07-28 | [7 empty] | Contingecy plan drafted
| Have single repository of governance materails per target audience | Develop and share governance sharepoint site for GC | 2023-01-01 |  | Update website to include all resolutions, signed minutes, adopted budgets, and applicable documents | 2023-03-01 |  | Continue to update website and sharepoint site | ongoing
| Assure secure storage of district electronic data | Provide cloud strorage of all district information thorugh MS365 | 2023-01-01 |  | Provide redundancies in data storage via external harddrive for all employees to back-up their desktop computer data | 2023-04-01 |  | Assure all destop/laptop computers have up-to-date firewall, anti-virus, and anti-spam software | 1/1/23 and ongoing |  | Set schedule for all employees to update firmware and OS and develop reporting system to demonstrate compliance | 2023-04-15 |  | All staff have external harddrive | Policy drafted
HUMAN RESOURCES | Have a strong understanding of tax law, benefits, etc as it relates to employee compensation | Identify and take course through LMC, edX, or hrtrainonline | 2022-09-01 |  | edX course - Public Financial Management | 2023-03-31
| Be able to evaluate staff performance in a manner that aids them in developing their skills to best benefit them and the district | Gain admission into BSU Public Administration Grad Certificate Program | Admitted for Summer '23
| Develop skill needed to handle difficult people calmly and professionally. | Identify and take course through LMC, edX, or hrtrainonline | 2023-05-01
| Gain a knowledge of fundamental aspects of personnel administration. eg. salary administration, position classification, performance appraisal, privacy, and harassment issues. | Gain admission into BSU Public Administration Grad Certificate Program | Admitted for Summer '23 |  | Begin Program | 2023-05-15 |  | Complete Program | Summer 2024
| Develop staff training and resources to facilitate an inclusive and safe workplace | Work with staff to develop work plans, including career goals and training opportunities | Ongoing - staff anniversaries |  | Find and provide access to human resource training as it realtes to DEI | Ongoing |  | Designate staff to be member of the MetroMAWD DEI Committee | 2023-01-01 |  |  |  |  | All staff will have individual workplans
| Gain a fundamental knowledge of applicable state statute. | Gain admission into BSU Public Administration Grad Certificate Program | Admitted for Summer '23 |  | Begin Program | 2023-05-15 |  | Complete Program | Summer 2024
| Act as staff liason to Personnel Committee | Attend personnel committee meetings | Ongoing |  | Provide materials and support to Personnel Committee as needed | Ongoing
| Have an updated Personnel Handbook that is reflective of current work environment and HR issues | Develop section on hybrid work policy | 2023-05-01 |  | Develop DEI section of Personnel Handbook | 2023-09-01 |  | Make other updates as needed | Ongoing |  |  |  |  | Completed section on hybrid work policy | Completed section on DEI
| Develop intitiatives to improve and maintain staff morale | Inqure with other watershed and municipal administrators/managers regarding their activities | 2023-04-14 |  | Bring in group facilitator to gain better understanding of workplace dynamics and interpersonal skills | 2023-08-01
| Have an efficient and effective onboarding program for new employees | Attend MAWD Annual Conference HR Session | 2023-12-02 |  | Request onboarding materials from other administrators | 2023-01-15 |  | Utilize MS365 Planner to develop onboarding plan | 2023-04-15
PLANNING & PARTNERSHIPS | Foster working relationship with community development departments of member cities. | Meet with city Community Development Departments | 2023-03-03 |  | Work to align Water Management Plan with city comprehensive plans | As plans come due
| Work to remove silos between parks, public works, planning, and public safety departments. | Coordinate and facilitate inter-departmental meetings. | Completion of Phase 1 of flood model
| Incorporate nature based solutions for climate resilience into the 10-year watershed management plan | Meet with Barr and staff to scope an outline of EHAP | 2022-12-15 |  | Meet with CAC to solicit input and subsequently present to BOM. | 2023-08-01
| Work to align respective capital plans of cities and district | Meet with PW and engineering staff to review multiyear CIP | 2023-06-01 |  | Update UAA to reflect current conditions and CIP alignment strategies | 2023-12-31
| Work with city staff and city subcommittees to assist in the implementation of their GreenStep cities initiatives. | Identify individual staff responsible for implementation | 2023-03-01 |  | Work with staff to identify gaps and areas for collaboration | 2023-05-01 |  | Meet with appropriate sub-committees to solicit input | Throughout 2023 |  | Meet with appropriate sub-committees to solicit input | Throughout 2023
| Work with Steve Christopher/Jennifer Mocol-Johnson (BWSR) to complete P-RAP | Meet with BWSR and provide list of partners | 2022-09-13 |  | Provide Water Plan Review to BWSR | 2022-10-05 |  | Present PRAP report to BOM | 2022-11-02 |  | Present PRAP report to BOM | 2022-11-02 |  | Partner List | Goals and Outcomes Review | Final PRAP Report
| Revise project prioritization metrics to consider nature based solutions and lessons learned | Incorporate district model, strategic plan, etc into suggested changes | To be done with in concert with EHAP |  | Engage TAC, CAC, and others | 2023-12-31 | [7 empty] | Technical memorandum of recommended changes
| Continue to participate in MAWA and MAWD. | Attend quarterly MAWA meetings | As scheduled |  | Volunteer to serve on sub-committee | 2023-01-01
| Foster Relationships with Lake Associations | Hold Lake Association Summit | 2023-04-11 |  | Attend annual events hosted by lake associations | As schedules |  | Work with LLCA to incoporate community feedback into lake management plan | 2023-01-31 |  | Engage at least one lake association to evaluate need for, and breadth of comprehensive lake management plan. | 2023-06-01 |  | Lake Association Summit Held | Knowledge of L.A. members | Section within LL Management Plan specific to community input
| Work with BOM on strategic planning efforts | Apply for PRAP Assistance Grant | 2022-12-02 |  | Solicit RFPs for strategic plan facilitation | TBD
| Open dialogue with community development departments at member cities | Send letter of introduction | 2023-03-01 |  | Hold TAP meeting with planners/CD staff as part of EHAP development | 2023-05-01
| Develop comprehensive, holistic plan that considers the impact of overall ecology on water resource protection - EHAP | Conduct kickoff meeting with team | 2023-02-23 |  | Determine advisory panel members | 2023-03-16 |  | Collect GIS data and develop maps | 2023-06-30 |  | Develop soil health framework, literature review, and field investigation | 2023-09-01
PROF DEVELOPMENT | Find HR professional/job coach to aid me in developing my interpersonal and management skills. | Identify individual/firm to serve in this capacity | 2023-04-01
| Obtain deeper knowledge and competence regarding administration o f government and non-profit organizations | Gain admission to BSU graduate certificate in Public/Non-profit Administration | 2023-03-15 |  | Begin coursework in program | 2023-05-15 |  | Complete Program | Fall 24 |  |  |  |  | Certificate
See other trainings in different groupings.
PROJECT MANAGEMENT | Lotus Lake Watershed Water Quality Improvement Project | Meet with Chanhassen parks, PW, and eng to scope project | 2022-09-15 |  | Develop feasibility study of potential practices and areas | 2023-04-01 |  | Develop cooperative agreement and regional stormwater plan with City of Chanhassen | 2023-09-30 |  | Order project
| Upper Riley Creek Stabilization and Ecological Enhancement | Complete EAW | 2022-08-01 |  | Meet with Chanhassen to discuss scope and other opportunities | 2002-10-01 |  | Develop cooperative agreement | 2023-02-01 |  |  |  |  | EAW submitted | Meeting(s) held | Cooperative agreement drafted
| Upper Bluff Creek Stabilization and Wetland Rehabilitation Project | Meet with Chanhassen to scope project | 2022-09-01 |  | Hold open house with area residents to solicit input and foster partnership | 2023-07-01 | [7 empty] | Meeting(s) held
| Wetland Assessment Program | Build phase I model | 2023-05-15 |  | Use soil health initiative and literature review component of EHAP to incoporate nutrient cycling and C sink into model | 2023-07-01 | [7 empty] | Strawman Model complete | Development of metrics and sampling protocol
| Ecological Enhancement Plan | Hold scoping meeting and bring scope to BOM | 2023-02-01 |  | Hold Kick-off meeting | 2023-03-01 |  | Establish sub-committee membership | 2023-03-01 |  | Provide data to Barr | TBD
| Lafe Susan Park Pond Re-use Maintenance | Meet with Chan Parks and Rec | 2023-01-15 |  | Bring work order to BOM | 2023-02-01 |  | Advertise for bid | 2023-03-01 |  | Complete work | 2023-05-15 |  | Meeting minutes | work order | bid docs/bid tab
REGULATORY | Develop cooperative relationships with city inspection programs | Identify MS4 inspectors for each partner city and introduce Mat | 2023-03-24 |  | Meet with inspectors to identify opportunities for collaboration and partnership
| Identify inefficiencies and gaps in regulatory program | Meet with legal counsel and district engineer to review existing rules and any needed changes | 2023-02-07 |  | Continue meeting with legal and engineering to assess needs | ongoing |  | Use EHAP findings to guide modifications of regulatory progam to meet updated policies, goals, and mission statement | TBD - 2024
| Have regulatory program be financial self-sustaining to the extent practicable | Review and update fee schedule and financial assurance schedule | 2022-12-28 |  | Present proposed 2023 schedules for board adoption | 2023-01-11
| Develop method for reporting inspection findings to all audiences | Oversee Natural Resources Tech's efforts to develop inspection reports | 2023-05-01